## work
DATE | JOB NO. | KIND OF WORK | BEGIN | FINISHED | HOURS
2020-03-05 | 1 | Replace mocking data with actual data to show fire stations' info when clicked. | 14:30 | 15:00 | 0.5
| 2 | Fix bug: The info window of previous marker doesn't close automatically when another marker is clicked. | 15:00 | 15:15 | 0.25
2020-03-09 | 1 | Fix bug: Remove previous marker when another accident spot is clicked. | 12:30 | 12:45 | 0.25
| 2 | New feature: Show nearest k fire stations | 12:45 | 13:45 | 1
| 3 | Fix bug: Restrict the map bounders | 14:00 | 14:15 | 0.25
| 4 | New feature: Add custom control panel | 13:45 | 15:00 | 1.25
| 5 | Transfer Nodes.xml to required format | 15:00 | 15:20 | 0.3
| 6 | Iterate through the node list to find the nearest node from the accident spot | 15:20 | 15:50 | 0.5
| 7 | Fix bugs: 1.Center Map will not zoom out. 2. Show All Stations will not zoom in. | 16:30 | 17:00 | 0.5
| 8 | Replace Accident Icon | 17:00 | 17:10 | 0.1
2020-03-11 | 1 | New feature: Show nearest k nodes besides the accident spot. | 14:30 | 17:30 | 3
2020-03-15 | 1 | Reasearch on how to interact when one wants to show routings from a target fire station | 19:00 | 21:00 | 2
2020-03-16 | 1 | Implement sidebar | 18:00 | 22:30 | 4.5
2020-03-18 | 1 | New feature: Routing | 14:30 | 17:30 | 3
| 2 | Fix bugs: duplicated info window | 17:30 | 18:30 | 1
| 3 | Change info window style | 18:30 | 19:15 | 0.75
2020-03-21 | 1 | Read XML into POJO | 23:30 | 1:30 | 2
2020-03-22 | 1 | Read XLSX into POJO | 1:30 | 3:30 | 2
| 2 | Merge files | 3:30 | 4:45 | 1.25
| 3 | Find nearest Link to accident spot | 15:50 | 17:50 | 2
2020-03-23 | 1 | Calculate sphere distance between two points, calculate distance between a point to a segment | 16:50 | 17:50 | 1
| 2 | Find nearest Link to accident spot - 2: Format path.json | 18:00 | 22:00 | 4
| 3 | Format nodes.json, Show nearest nodes inside circle. | 23:00 | 1:00 | 2
2020-03-24 | 1 | Format paths.json | 16:00 | 18:00 | 2
| 2 | Find nearest path to accident spot | 18:00 | 19:00 | 1
| 3 | Draw the nearest path | 19:10 | 20:10 | 1
2020-03-29 | 1 | Change sidebar presentation | 1:15 | 14:30 | 1.25
| 2 | Click the sidebar interaction | 17:00 | 18:00 | 1
| 3 | Change click sidebar interaction | 20:20 | 21:50 | 1.5
2020-03-31 | 1 | Sidebar add sub list | 21:45 | 23:20 | 1.5
2020-04-01 | 1 | debug | 12:25 | 14:00 PM | 1.5
| 2 | Finish modify sidebar | 18:30 | 22:30 | 4
2020-04-02 | 1 | Skype meeting with Hassan | 15:45 | 16:15 | 0.5
| 2 | Travel time and risk | 16:20 | 17:00 | 0.5