## Product Backlog
Phase | User Story | Theme | AS a/an | I want to… | so that… | Notes | Priority | Status
1(about 3 weeks) | 1 | website | website user | access the map application by visiting the URL in the Internet explorer | I can see the whole map of Dallas area | Show only the map of the DFW area with borders restricted, No other part will be contained | 1 | todo
| 2 | website | website user | move the direction of the map and zoom in and out | I can locate any location I want | User can move the map towards different directions and zoom in and out with the mouse pointer | 2 | todo
| 3 | website | website user | touch any position on the map | I can point out this is an accident spot |  | 3 | todo
| 4 | website | website user | see the locations of the nearest rescue stations of the accident spot that I pointed out | I will have a whole view of where the stations are around the accident spot |  | 4 | todo
| 5 | website | website user | see the paths between the rescue stations with the accident spot | I will have a concrete view of all the paths |  | 5 | todo
| 6 | website | website user | see the driving time of every path | I will know if the path is near or far away |  | 6 | todo
| 7 | website | website user | see the traffic risk of every path | I will know if the traffic condition of each path is good or not |  | 7 | todo
2 | 8 | website | website user | see the 3D model of the positions on the map | I can recognize the real appearance of the locations in reality |  | 8 | todo
| 9 | website | website user | see the 3D model of every rescue path | I will have a better impression on the path which will surely navigate me to the right way |  | 9 | todo
3 | 10 | app | app user | access the service via my iphone | I can use the service no matter where I am | This is the basic step to set up the app on the iOS platform | 10 | todo
| 11 | app | app user | access the service via my android phone | I can use the service no matter where I am | This is the basic step to set up the app on the android platform (I'm not sure if we do on both platform or not, the work may not just copy and paste due to the restrictions of the two different platform) | 10 | todo
| 12 | app | app user | access the map of the entire DFW area | I can see the whole map of Dallas area on my phone |  | 11 | todo
| 13 | app | app user | move the direction of the map and zoom in and out | I can locate any position I want |  | 12 | todo
| 14 | app | app user | see my own location on the map | I know where I am |  | 13 | todo
| 15 | app | app user | touch any position on the map | I can point out this is an accident spot |  | 14 | todo
| 16 | app | app user | see the locations of the nearest rescue stations of the accident spot that I pointed out | I will have a whole view of where the stations are around the accident spot |  | 15 | todo
| 17 | app | app user | see the paths between the rescue stations with the accident spot | I will have a concrete view of all the paths |  | 16 | todo
| 18 | app | app user | see the driving time of every path | I will know if the path is near or far away |  | 17 | todo
| 19 | app | app user | see the traffic risk of every path | I will know if the traffic condition of each path is good or not |  | 18 | todo
| 20 | app | app user | see the 3D model of the positions on the map | I can recognize the real appearance of the locations in reality |  | 19 | todo
| 21 | app | app user | see the 3D model of every rescue path | I will have a better impression on the path which will surely navigate me to the right way |  | 20 | todo

## Sprint1 Backlog
ID | Phase | User Story | Task | Notes | Priority | Estimated Time(day) | Status
1 | 1 | access the map application by visiting the URL in the Internet explorer | 1.set up the web server using node.js 2.give a simple default page |  | 1 | 1 | todo
2 | 1 |  | 1.design the outline of the functional page using React.js |  | 2 | 1.5 | todo
3 | 1 | move the direction of the map and zoom in and out | 1.embeded Google Map into the page 2.restrict the border of the map only showing the DFW area |  | 3 | 2 | todo
4 | 1 |  | 1.move 2.zoom in and out |  | 4 | 0.5 | todo
5 | 1 |  | 1.show all rescue stations on the map after the page initialization | 1.parse the JSON file to find out all the rescue stations 2.draw indicators on the top of all the stations 3.show the names of these stations | 5 | 3 | todo
6 | 1 | touch any position on the map | 1.draw an indicator on the top of the position 2.show the details of the position where the pointer is clicked on | details contain: name, address, geography info(if needed) | 6 | 2 | todo
7 | 1 | see the locations of the nearest rescue stations of the accident spot that I pointed out | 1.get the longitude and latitude of the accident spot 2.deserialize the whole JSON file to object 3.search the object for all the pairs whose destination indicates matching |  | 7 | 2 | todo
8 | 1 |  | 1.get all the longitude and latitude of the from-point(s) in these pairs 2.draw indicators on the top of these from-point(s) 3.show the name of these rescue stations |  | 8 | 1 | todo
9 | 1 | see the paths between the rescue stations with the accident spot | 1.get the points of each path from the deserialized JSON object 2.use these points to draw the path | Find out the solution of how to draw the path according to these points | 9 | 3 | todo
10 | 1 | see the driving time of every path | 1.get the driving time of all the path from the object 2.show the time on the map |  | 10 | 2 | todo
11 | 1 | see the traffic risk of every path | 1.get the traffic risk(s) of all the path from the object 2.use different colors or symbols to indicate these traffic risk(s) |  | 11 | 2 | todo
12 |  | access the map of the entire DFW area |  |  | 11 |  | todo
13 |  | move the direction of the map and zoom in and out |  |  | 12 |  | todo
14 |  | see my own location on the map |  |  | 13 |  | todo
15 |  | touch any position on the map |  |  | 14 |  | todo
16 |  | see the locations of the nearest rescue stations of the accident spot that I pointed out |  |  | 15 |  | todo
17 |  | see the paths between the rescue stations with the accident spot |  |  | 16 |  | todo
18 |  | see the driving time of every path |  |  | 17 |  | todo
19 |  | see the traffic risk of every path |  |  | 18 |  | todo
20 |  | see the 3D model of the positions on the map |  |  | 19 |  | todo
21 |  | see the 3D model of every rescue path |  |  | 20 |  | todo

## Dropdown list elements
status list elements | theme list elements | user list elements | phase list elements
done | website | website user | 1
todo | app | app user | 2
doing |  |  | 3

## Problem Record
Date | Content | Solution

## Backlog Properties
Product Backlog properties
1 | single source of requirements of any changes
2 | responsible by Product Owner: content, availability and ordering
3 | dynamic, never complete
4 | evolves as the product and environment will be used to evolve
5 | ongoing backlog refinement: review and revise